## Sheet1
Customer selections and meetings during the SHB building process.
While we are preparing to break ground: | Additional Notes:
1. Meet with our Building Supply salesman (Kenney with ADK Building Supply) | I will give him your number to call and set up an appointment. He already has a copy of your plans.
2. Select plumbing fixtures | Lewis - Smith Supply - take your plans. You may decide to get your sinks from the granite place (usually cheaper). All other plumbing fixtures here. Freestanding tubs and farm sinks are often purchased online. Ask Scott for guidance.
3. Select your Brick | Acme Brick. Whatley Brick can also be a choice. You're welcome to look at flooring while there, but it isn't necessary at this time.
While your house is being framed: | Additional Notes:
1. Plan for the cable, phone, and data locations. Any specialty wiring such as surround sound and camera systems? | We will meet on site and mark the locations of cable/phone/data outlets on the wall, and make sure an electric outlet is near the desired cable outlets.
2. Hopefully you have no electrical changes from the plans. But if you do, please keep a list and we will set up a meeting with the electrician. | This meeting with the electrician will also be a good time to discuss a pool and a detached shop (if applicable), or any other special electrical considerations. Let him (and us) know if you want to upgrade any bath fans, smoke detectors, dimmer switches, etc. SHB also recommends that you consider LED mini-flush lights instead of traditional recess housings-can lights. Ask us about it, if you have any questions.
3. Let us know if you have any particular wish for where these are located: air conditioner, water heater, water panel, electric panel, security panel and equipment, gas tank, generator, anything else applicable. | Our tradesmen will decide on the best location of each, if the customer has no particular concern. Usually the tradesmen know the best locations, but most of the time we can still accommodate the customer's wishes.
Before drywall starts: | Additional Notes:
1. Meet with the cabinet guy. | We will meet on site and discuss everything with our cabinets. We will walk through and discuss all considerations. Let us know when you are ready to meet.
2. Plan for any trim details or changes from the contract | Discuss with SHB if you are doing anything different than the original contract. IF you have a barn door, talk to Scott about online options.
3. Pick paint colors | Sherwin-Williams (give them your name, address, and SHB). They will put all your info into a file for us. Will need to select: 1. ceiling color (usually flat white). 2. Trim color (usually semigloss white or off white). 3. Wall colors. 4. Cabinet colors. 5. Front door stain or paint color. 6. All other exterior door colors. 7. Stain or paint colors for any outside features such as columns, shutters, beams, or gable accents. 8. Stain or paint colors for any inside special features such as stairs, beams, columns, or ceilings.
4. Select tile | Acme Brick and Tile - take your plans. Remember to select from the master shower tile too. Kitchen cabinet backsplash also, if included in the contract.
5. Select light fixtures | Mayer Lighting Showroom - take your plans. Let them know if you want upgraded bulbs and pricing, or they will send standard.
6. Select counter tops (granite is most common) | Carpetland There are about 7 granites that are in the $35 per foot price range, because they are common to many mountains (granite is carved out of mountains). Everything else will come from a unique mountain somewhere in the world and the price will reflect how far away that mountain is. Let us know when your selection is made so we can send them out to measure for the tops.
While the house is being painted: | Additonal Notes:
1. Select hardwood or vinyl plank flooring | Acme Brick and Tile. Carpetland. If plank is desired, talk to Scott about his experience. Vinyl plan has become extremely popular, and thusly become more complicated. Scott has strong opinions and experience about plank flooring that can go beyond the sales pitch. If you are choosing hardwood, please discuss that with Scott also.
2. Select appliances | Brackin Appliance. The fridge, washer, and dryer need to wait until the home is complete, if you end up buying them too. Please plan to call them back and set up that delivery to be in proximity of your move in date. If you select your appliances somewhere else, just make sure they will hold them until we are ready.
3. Select cabinet hardware | Brackin Wholesale (they have a display room and they will leave your selections on file for the cabinet guy) The display items are included. Special order stuff will probably cost extra. IF you have a mud cabinet, they don't really carry a selection of coat hooks. If you go to the big box store and purchase, we will install for you. Simply mark the locations with painters tape, and we will handle it. Same for any barn door hardware.
4. Select Carpet | Carpetland. We really believe in Friese carpet with speckles. The Speckles help with stains and the fries seems to be the best choice to resist traction.
After the master shower is tiled: | Additional Notes:
1. Plan closet shelving, mirrors, bath hardware, and shower door. | We will meet with B and W at the house. Let us know what day works for you to set up an appointment. There will be choices to upgrade or add services with this company (they offer several home services), but please request pricing in advance. It's all small stuff, but it can add up.
2. Plan the driveway or parking pad | Meet with our superintendent and bring a drawing of what you are thinking. Don't worry, you don’t have to be a good artist, but drawings help us read your mind!
3. Pick gas logs and propane tank | Only applicable to homes with gas or propane.
After the driveway is poured: | Additional Notes:
1. Plan any landscaping, irrigation, or flower beds | Let us know what day will work best for meeting our landscape contractor. We will meet at the house.
2. Final walk through… Not really! | At this point you have probably walked through the house a 100+ times. You have brought concerns to our attention, and we have hopefully addressed them satisfactorily. At this point, remind us or ask us if your concern is still on our to do list. SHB will never want to conduct a final walk through on the last day, because that procrastination would only create an annoying delay. Why wait until the end? At that point, we want you to move in and enjoy your new home!
Special Notes:
1. You can always get ahead of this schedule if you are eager! Call and we point you in the right direction.
2. After the permanent power is connected (after the lights are hung), contact your lender and begin discussions of closing procedures. You are probably 30 to 60 days from completion.
3. Let us know if you have any problems with selections or any of our vendors. Definitely let us know if you are not satisfied with the service.
4. Please enjoy the process! But don’t let yourself get too far off budget without realizing. Remember that the allowance was set according to the budget mindset you had when you started talking to SHB about your new home.
5. Please treat our subcontractors and vendors with ultimate respect. Without them, our dream home could never exist. They are human and could make a mistake, but be assured that they are the best that exist in this market. For them to be working for us, it means they have already earned respect and credibility . Please be patient if a situation ever arises and give them a chance to make it right. There is nothing perfect about a human built home, but these guys know how important it is to you and they are going to do their best to make you very happy.
6. Please enjoy the decision making process. It's not always easy, but it's never as consequential as you may think it is while you are in your moments of stress. Your home is going to be great with any of the considerations you are stressing over. Remind yourself that a beautiful home is a blessing, but it is not even close to the true relevance of your life!
7. We pride ourselves on being the best. And that is because we care the most. We will always have ultimate concern for your satisfaction. But, we know that the reality is that no home is ever close to perfection. The best home we have ever built has many imperfections, as well as any other house that has ever been built. Perfection does not exist. If you put on your magnifying glasses and seek all our imperfections, I'm sure you will find them, but you will also get yourself convince yourself that your beautiful home is not what is actually is, the most perfect home that you planned for your family.